## Schedule
| Week No. | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | Legend | Deadlines |  | TEAM A | Juan Valencia Zuleta
No. | Date | 2019-10-24 | 2019-10-31 | 2019-11-07 | 2019-11-14 | 2019-11-21 | 2019-11-29 | 2019-12-05 | 2019-12-12 | 2019-12-19 | 2019-12-26 | 2020-01-02 | 2020-01-09 | 2020-01-17 | 2020-01-23 | Everybody | 2020-01-12 | 12pm. Submit Report by email |  | Ahmad Shatnawi
1 | General Research | [14 empty] | Team A | 2020-01-17 | Presentation |  | Malik Javadov | bar: 2019-10-24 to 2019-11-07
2 | Machine Vision Research | [14 empty] | Team B | 2020-01-23 | Presentation | bar: 2019-11-07 to 2019-11-21
3a | Machine Vision Codes | [14 empty] | Team C |  |  | TEAM B | Kanan Karimli | bar: 2019-11-29 to 2019-12-12
3b | Simulation Environment | [18 empty] | Komal Suryawanshi | bar: 2019-11-29 to 2019-12-12
3c | Creating QR Code Reader | bar: 2019-11-29 to 2019-12-12
4 | Running Simulation Tests | [17 empty] | TEAM C | Amrith Venkat Kesavamoorthi | bar: 2019-12-19 to 2019-12-26
5 | Running Real Tests | [18 empty] | Ranjith Mahendran | bar: 2020-01-02 to 2020-01-09
6 | Writing the Report | bar: 2019-11-14 to 2020-01-17
7 | Presentation | bar: 2020-01-17 to 2020-01-23
Research: Ubuntu, Linux commands, ROS, GitLab and NextCloud.
Research: Machine Vision, Image Processing, Ackerman Steering, data subscriptionn Arduino, PWM, C++ and Python.
Learning about math operations and filters. (Mean, median, noise reduction, thresholding, blobs, characteristics, geometry calculation, etc).
Creating a Hello World Program.
Connecting the webcam and given camera to ROS.
Taking a random fixed set of pictures.
Applying filters to the pictures.
Creating live connection with the onboard camera.
Applying same filters to the live connection.
Learning how fast is the processing and how much FPS are lost with every filter addition.
Research: Diffferent methods of Lane Detection.
Defining an optimal combination of Image quality and Speed (FPS) based on desired driving speed.
Discussing with team members algorithms for Lane Detection.
Taking a new specific set of test images including working elements: tracks, lanes, QR signs, other cars, etc.
Writing algorithms that are able to identify the working elements. (Object Identification Algorithm)
Trying out the algorithms on the test images.
Writing algorithms that manually drives the car. (Steering Angles Algorithm)
Trying out the Steering Angle algorithm on the car.
Writing code that use the identified working elemenet as input and outputs a steering angle. (Mixing both previous algorithms).
Goal 3a: Lane Following Algorithm.
Goal 3a: Lane Changing Algorithm.
Learn how to create simulations using ROS.
Select the correct track objects from the library.
Select the correct car, steering type and dimensions.
Select different simulation cameras.
Goal 3b: Create different courses (Racing tracks) with varying difficulties and working elements.
Download different QR libraries and use them.
Test the libraries with sample images.
Test the code in the real onboard camera and different webcam cameras.
Unify the code to create a single universal QR reader.
Goal 3c: Modify the Universal QR Reader so that it works at varying distances (far and close to the camera).
Testing out the algorithms into the different Racing Tracks Simulations.
If the simulation fails, find the source of error and fix it on the car or simulation side and try again. Repeat until all algorithms are able to pass all the simulations multiples times consecutively.
Goal 4: Speed up and fix algorithms. Pass the simulation tests.
Test everything at minimun speed on the car.
If algorithms fails, find the error, fix it and try again.
if algorithm is succesful, increase the speed and try it again.
Goal 5: Repeat this process until the desired speed is achieved. Pass the real tests. (Max speed: 40km/h)
Goal 6: Report submission.
Goal 7: Presentation.