## Schedule
Week No. | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | Legend | Deadlines
Date | 2024-10-01 | 1931-10-01 | 2007-11-01 | 2014-11-01 | 2021-11-01 | 2028-11-01 | 2005-12-01 | 2012-12-01 | 2019-12-01 | 2026-12-01 | 2002-01-01 | 2009-01-01 | 2017-01-01 | 2023-01-01 | Everybody | 2012-01-01 | 12pm. Submit Report by email
Ubuntu & ROS Installation and Research | [14 empty] | Team A | 2017-01-01 | Presentation
Machine Vision Research & Discussion | [14 empty] | Team B | 2023-01-01 | Presentation
Creating Machine Vision Codes | [14 empty] | Team C
Creating Simulation Environment
Creating QR Code Reader
Running Simulation Tests
Running Real Tests
Writing the Report
Presentation
Reading about Ubuntu.
Learning Linux commands.
Reading about ROS.
Learning how to use ROS.
Llearning about Machine Vision and Image processing.
Learning about math operations and filters. (Mean,median, noise reduction, thresholding, blobs, characteristics, geometry calculation, etc)
Learning about C++ or Python.
Connecting the webcam and given camera to ROS.
Taking a random fixed set of pictures.
Applying filters to the pictures.
Creating live connection with the onboard camera.
Applying same filters to the live connection.
Learning the steering system with Arduino driven by data.
Learning how fast is the processing and how much FPS are lost with every filter addition.
Researching diffferent methods of Lane Detection.
Defining an optimal combination of Image quality and Speed (FPS) based on desired driving speed.
Discussing with team members algorithms for Lane Detection.
Taking a new speecific set of test images including working elements: tracks, lanes, QR signals, other cars, etc.
Writing algorithms that are able to identify the working elements.
[5 empty] | Team A | Trying out the algorithms on the test images.
Writing algorithms that manually drives the car. (Steering Angles)
Trying out the Steering Angle algorithm on the car.
Writing code that use the identified working elemenet as input and outputs a steering angle. (Mixing both previous algorithms).
Writing an algorithm for following the lane. GOAL 1.
Writing an algorithm for lane change. GOAL 2.
Learn how to create simulations using ROS.
Select the correct track objects from the library.
[5 empty] | Team B | Create the correct car drriving type and dimensions.
Select different simulation cameras.
Create different courses (Racing tracks) with varying difficulties and working elements.
Download different QR libraries and use them.
Test the libraries with sample images.
[5 empty] | Team C | Test the code in the real onboard camera and different webcam cameras.
Unify the code to create a single universal QR reader.
Modify the code so that it works at varying distances (far and close to the camera).
Testing out the algorithms into the different Team B Simulations.
If the simulation fails, find the source of error and fix it on the car or simulation side and try again. Repeat until all algorithms are able to pass all the simulations multiples times consecutively.
Speed up and fix algorithms.
Test everything at minimun speed on the car.
If algorithms fails, find the error, fix it and try again.
if algorithm is succesful, increase the speed and try it again.
Repeat this process until the desired speed is achieved.
Report submit.
Presentation.